## Sheet1
Task | Start | DueDate | Length
Project Kick-off & Scope Definition | 2025-09-08 | 2025-09-11 | 3
System Analysis & Conceptual Design | 2025-09-12 | 2025-09-19 | 7 | 45908 | 45942
User Interface Prototype Construction | 2025-09-20 | 2025-09-30 | 10
Sample Data Setup & Basic Configurations | 2025-10-01 | 2025-10-05 | 4
Quality Check & Usability Walkthrough | 2025-10-06 | 2025-10-09 | 3
Final Write-up & Submission Prep | 2025-10-10 | 2025-10-12 | 2